## Stakeholders
stakeholder_id | role | responsibilities | pain_points | expectations | influence | interest | communication_plan
STK-01 | Executive Sponsor (COO) | Own business case, funding, adoption mandate, and enterprise outcome accountability. | Missed cross-functional commitments, delayed decisions, weak visibility into silent execution risk. | Executive risk view, measurable productivity gains, clear governance. | High | High | Monthly steering committee; quarterly value realization review.
STK-02 | Product Owner | Prioritize roadmap, accept stories, resolve scope decisions, manage product outcomes. | Fragmented requests and limited evidence for prioritization. | Traceable backlog, rapid feedback, measurable adoption. | High | High | Twice-weekly refinement; sprint review and release readiness.
STK-03 | Enterprise Architecture | Approve integration, identity, data, platform, and non-functional architecture. | Point-to-point integrations and ungoverned AI services. | Reusable APIs, event-driven patterns, approved cloud controls. | High | Medium | Architecture review at discovery, design, and pre-production gates.
STK-04 | Information Security | Threat modeling, IAM, encryption, vulnerability and incident controls. | Sensitive message content and excessive permissions. | Least privilege, tenant isolation, security logging, evidence. | High | Medium | Biweekly security workstream; formal control sign-off.
STK-05 | Privacy & Legal | Define lawful processing, consent, retention, discovery, and acceptable monitoring boundaries. | Employee surveillance risk and cross-border data handling. | Purpose limitation, configurable retention, data subject controls. | High | High | Weekly policy workshop during design; monthly compliance review.
STK-06 | Data Governance Council | Approve data definitions, stewardship, lineage, quality and reference data. | Inconsistent ownership, status and SLA definitions. | Certified KPI glossary, lineage, data quality thresholds. | Medium | High | Biweekly data governance forum; certification before launch.
STK-07 | Department Heads | Drive adoption, act on escalations, monitor team performance. | Late surprises and manual status chasing. | Department dashboards, drill-down, fair accountability measures. | High | High | Monthly business review; targeted adoption digest.
STK-08 | Managers / Team Leads | Review team commitments, reassign work, manage exceptions. | Multiple tools and unclear ownership. | Actionable queue, low-noise reminders, bulk triage. | Medium | High | Pilot office hours; weekly usage insights.
STK-09 | Employees / Promise Owners | Confirm, update, fulfill, reassign, or dispute detected promises. | Manual task entry, notification fatigue, false positives. | Transparent AI reasoning, easy correction, privacy safeguards. | Medium | High | In-product onboarding, FAQs, feedback channel, pulse surveys.
STK-10 | Integration Engineering | Build and operate connectors, webhooks, replay, throttling and monitoring. | API rate limits, schema drift, token expiry. | Clear contracts, observability, idempotency. | Medium | High | Daily stand-up during integration sprints; weekly API review.
STK-11 | Data Science / ML | Build extraction, classification, prediction, evaluation and model monitoring. | Limited labeled data and changing language patterns. | Human feedback loop, model registry, evaluation dataset. | Medium | High | Weekly model review; monthly bias and drift review.
STK-12 | Support & Platform Operations | Incident response, support, runbooks, availability and capacity. | Hard-to-diagnose ingestion and notification failures. | SLOs, dashboards, replay tools, clear ownership. | Medium | Medium | Operational readiness reviews; weekly service report after launch.

## RACI
activity | Executive Sponsor | Product Owner | Business Analyst | Solution Architect | Engineering Lead | ML Lead | Security | Privacy/Legal | Data Governance | QA Lead | Change Lead | Operations
Business case and funding | A | R | C | C | I | I | C | C | I | I | C | I
Scope and product roadmap | C | A | R | C | C | C | C | C | C | I | C | I
Requirements baseline | I | A | R | C | C | C | C | C | C | C | C | I
Integration architecture | I | C | C | A | R | I | C | C | C | C | I | C
AI model design and evaluation | I | A | C | C | C | R | C | C | C | C | I | I
Security and threat model | I | C | C | C | C | C | A/R | C | I | C | I | C
Privacy impact assessment | I | C | C | C | I | C | C | A/R | C | I | C | I
Data model and KPI certification | I | C | R | C | C | C | C | C | A | C | I | I
Build and configuration | I | A | C | C | R | R | C | C | C | C | I | C
System and integration testing | I | C | C | C | C | C | C | C | C | A/R | I | C
UAT and business acceptance | C | A | R | C | C | C | C | C | C | R | C | I
Training and adoption | I | C | C | I | I | I | I | C | I | C | A/R | C
Production readiness and support | I | C | C | C | R | C | C | C | I | C | C | A
Value realization | A | R | C | I | I | I | I | C | C | I | C | C

## Business_Requirements
requirement_id | name | requirement | moscow | owner | status | version
BR-001 | Unified Communication Ingestion | The platform shall securely ingest supported messages, transcripts, comments and notes from approved enterprise systems. | Must | Executive Sponsor | Approved for Portfolio Baseline | 1.0
BR-002 | Automated Promise Detection | The platform shall detect explicit and implicit business commitments from ingested content using governed AI models. | Must | Product Owner | Approved for Portfolio Baseline | 1.0
BR-003 | Promise Ledger Creation | Each confirmed commitment shall be stored as a uniquely identifiable business object linked to source evidence. | Must | Product Owner | Approved for Portfolio Baseline | 1.0
BR-004 | Owner Identification | The platform shall identify the accountable individual or team and allow confirmation or correction. | Must | Department Heads | Approved for Portfolio Baseline | 1.0
BR-005 | Deadline Extraction | The platform shall resolve explicit, relative and contextual deadlines using user locale, working calendars and source time zone. | Must | Product Owner | Approved for Portfolio Baseline | 1.0
BR-006 | Lifecycle Management | Users shall transition commitments through Open, In Progress, Fulfilled, Reassigned, Delayed, Cancelled, Overdue and Escalated states. | Must | Operations | Approved for Portfolio Baseline | 1.0
BR-007 | Contextual Notifications | The platform shall deliver configurable reminders and follow-ups through in-app and approved source channels. | Must | Department Heads | Approved for Portfolio Baseline | 1.0
BR-008 | Escalation Management | The platform shall apply SLA and risk-based escalation policies with manager and project routing. | Must | COO | Approved for Portfolio Baseline | 1.0
BR-009 | Enterprise Search | Authorized users shall search and filter commitments by text, owner, department, project, source, status, date and risk. | Must | Employees | Approved for Portfolio Baseline | 1.0
BR-010 | Role-Based Dashboards | The platform shall provide persona-specific dashboards for executives, managers and individual employees. | Must | COO | Approved for Portfolio Baseline | 1.0
BR-011 | Scheduled Reporting | The platform shall generate weekly, monthly, quarterly, operational, risk and compliance reports. | Should | Department Heads | Approved for Portfolio Baseline | 1.0
BR-012 | Human Review and Dispute | Users shall confirm, edit, reject, merge or dispute AI-detected commitments with reason capture. | Must | Privacy & Legal | Approved for Portfolio Baseline | 1.0
BR-013 | Access Control | The platform shall enforce SSO, RBAC, row-level security, source permissions and segregation of duties. | Must | Information Security | Approved for Portfolio Baseline | 1.0
BR-014 | Immutable Auditability | All creation, edits, AI decisions, ownership changes, notifications and exports shall be auditable. | Must | Compliance | Approved for Portfolio Baseline | 1.0
BR-015 | Privacy and Retention | The platform shall support configurable retention, legal hold, minimization, redaction and regional processing controls. | Must | Privacy & Legal | Approved for Portfolio Baseline | 1.0
BR-016 | Analytics and Export | Authorized users shall access certified KPIs and export governed datasets to approved BI tools. | Should | Data Governance | Approved for Portfolio Baseline | 1.0
BR-017 | Learning Feedback Loop | User corrections shall be captured as labeled feedback for monitored model improvement without automatic unsafe retraining. | Should | Data Science | Approved for Portfolio Baseline | 1.0
BR-018 | Administration and Configuration | Administrators shall manage integrations, policies, reference data, notification templates, feature flags and model thresholds. | Must | Platform Operations | Approved for Portfolio Baseline | 1.0

## Functional_Requirements
requirement_id | name | requirement | parent_br | priority | epic_id | dependency
FR-001 | Connector Registration | Admin registers a source connector, scopes permissions, validates credentials and activates ingestion. | BR-001 | Must | E1
FR-002 | Incremental Ingestion | System ingests new and changed content using webhooks or checkpoints without duplicate processing. | BR-001 | Must | E1
FR-003 | Ingestion Replay | Authorized support users replay failed ingestion from a durable checkpoint. | BR-001 | Should | E1
FR-004 | Content Normalization | System maps source payloads to a canonical conversation and message model. | BR-001 | Must | E1
FR-005 | Language Detection | System identifies supported language and routes unsupported content to configured handling. | BR-002 | Should | E2
FR-006 | Promise Candidate Extraction | AI returns promise text span, type, owner candidate, deadline candidate and confidence. | BR-002 | Must | E2
FR-007 | Confidence Policy | System auto-creates, queues for review, or suppresses a candidate based on configurable thresholds. | BR-002 | Must | E2
FR-008 | Evidence Link | Promise record displays source message, surrounding context and immutable source reference. | BR-003 | Must | E3
FR-009 | Owner Resolution | System resolves people and teams using directory, aliases, conversation membership and project context. | BR-004 | Must | E2
FR-010 | Owner Confirmation | Detected owner can accept, reject, delegate or propose a corrected owner. | BR-004 | Must | E3
FR-011 | Deadline Resolution | System converts relative language to a timestamp using business calendar, locale and time zone. | BR-005 | Must | E2
FR-012 | Ambiguous Deadline Review | Ambiguous dates are flagged and require user confirmation before SLA enforcement. | BR-005 | Must | E3
FR-013 | Status Transition | Users update commitment status subject to state-transition rules. | BR-006 | Must | E3
FR-014 | Ownership Reassignment | Authorized users reassign commitment with reason, effective time and notification. | BR-006 | Must | E3
FR-015 | Delay / Due Date Change | Owner requests a due-date change; system captures reason and optional manager approval. | BR-006 | Should | E3
FR-016 | Reminder Scheduling | System schedules reminders by priority, due date, risk score and user preferences. | BR-007 | Must | E4
FR-017 | Escalation Rules | System evaluates overdue, risk, dependency and inactivity conditions and creates escalation events. | BR-008 | Must | E4
FR-018 | Notification Actions | Recipients can open, snooze, update, reassign or complete from supported notification surfaces. | BR-007 | Should | E4
FR-019 | Search and Filters | Users search full text and apply compound filters with saved views. | BR-009 | Must | E5
FR-020 | Conversation Timeline | Promise detail shows chronological source messages, lifecycle events, reminders and decisions. | BR-003 | Must | E5
FR-021 | Executive Dashboard | Executives view enterprise completion, aging, SLA, risk and trend KPIs with drill-down. | BR-010 | Must | E6
FR-022 | Manager Dashboard | Managers view team workload, overdue items, ownership changes and bottlenecks. | BR-010 | Must | E6
FR-023 | Employee My Commitments | Employees view commitments they own, owe, follow, or recently completed. | BR-010 | Must | E6
FR-024 | Scheduled Reports | Authorized users schedule reports with filters, format, recipients and delivery channel. | BR-011 | Should | E6
FR-025 | AI Review Queue | Reviewers approve, edit, reject, merge and label false positive/negative reasons. | BR-012 | Must | E2
FR-026 | Dispute Workflow | A disputed promise is frozen from punitive metrics until reviewed under policy. | BR-012 | Must | E3
FR-027 | RBAC and Row Security | Access is evaluated from enterprise identity, source ACLs, role and organizational hierarchy. | BR-013 | Must | E7
FR-028 | Audit Search and Export | Compliance users query and export immutable audit events under approved purpose. | BR-014 | Must | E7
FR-029 | Retention and Legal Hold | Data is deleted or retained according to source, region, record type and legal hold. | BR-015 | Must | E7
FR-030 | Admin Configuration | Admin manages thresholds, SLAs, calendars, templates, reference data and feature flags. | BR-018 | Must | E8

## Nonfunctional_Reqs
requirement_id | category | requirement | parent_br | priority
NFR-001 | Availability | Core ledger and API services shall achieve 99.9% monthly availability; reporting may operate at 99.5%. | BR-010 | Must
NFR-002 | Performance | P95 ledger search shall complete within 2 seconds for standard filters; P95 promise detail within 1.5 seconds. | BR-009 | Must
NFR-003 | Ingestion Latency | 95% of webhook-supported messages shall be normalized within 5 minutes; batch connectors within 30 minutes. | BR-001 | Must
NFR-004 | Scalability | Architecture shall support 25,000 users, 20 million messages/month and 250,000 active promises without redesign. | BR-001 | Should
NFR-005 | Security | Data shall be encrypted in transit and at rest using enterprise-approved algorithms and managed keys. | BR-013 | Must
NFR-006 | Identity | SSO shall support OIDC/SAML, MFA enforcement and SCIM lifecycle provisioning. | BR-013 | Must
NFR-007 | Audit | Audit events shall be append-only, time-synchronized, queryable and retained for seven years where required. | BR-014 | Must
NFR-008 | Privacy | Sensitive content shall support masking, minimization, regional routing and configurable retention. | BR-015 | Must
NFR-009 | Accessibility | User interfaces shall conform to WCAG 2.2 AA for supported workflows. | BR-010 | Must
NFR-010 | Observability | Services shall emit structured logs, metrics and traces with correlation IDs and privacy-safe fields. | BR-014 | Must
NFR-011 | Recovery | RPO shall be 15 minutes and RTO 4 hours for production ledger services. | BR-010 | Must
NFR-012 | Interoperability | APIs shall use versioned REST/JSON contracts and event schemas with backward compatibility policy. | BR-016 | Should
NFR-013 | Model Quality | Production promise detection shall maintain precision >= 0.88 and recall >= 0.80 on the governed evaluation set. | BR-002 | Must
NFR-014 | Explainability | AI decisions shall expose evidence span, extracted fields, confidence and model version to authorized users. | BR-012 | Must
NFR-015 | Maintainability | Critical services shall meet automated test, code quality and deployment rollback standards. | BR-018 | Should

## Epics
epic_id | epic_name | outcome
E1 | Secure Omnichannel Ingestion | Approved enterprise content arrives reliably in a canonical schema with replay and observability.
E2 | AI Commitment Intelligence | Commitments, owners, deadlines, types and risks are extracted with governed human review.
E3 | Promise Ledger and Workflow | Every confirmed promise has evidence, accountable ownership and a controlled lifecycle.
E4 | Notifications and Escalations | Timely, low-noise interventions reduce forgotten and overdue commitments.
E5 | Search and Conversation Context | Users can locate commitments and understand the complete conversation trail.
E6 | Analytics, Dashboards and Reporting | Personas receive trusted KPIs and actionable operational insight.
E7 | Security, Privacy and Compliance | Access, retention, audit and employee monitoring controls are enterprise-ready.
E8 | Administration and Platform Operations | Platform teams can configure, operate, support and evolve OpenLoop safely.

## User_Stories
story_id | epic_id | user_story | moscow | story_points | primary_fr | invest | status | release
US-001 | E1 | As an integration administrator, I want to register a Slack workspace with approved scopes so that OpenLoop can ingest only authorized content. | Must | 8 | FR-001 | Pass | Ready for Refinement | MVP
US-002 | E1 | As a platform operator, I want idempotent checkpoint processing so that retries do not create duplicate messages or promises. | Must | 8 | FR-002 | Pass | Ready for Refinement | MVP
US-003 | E1 | As support staff, I want to replay a failed ingestion window so that missing source content can be recovered without engineering intervention. | Should | 5 | FR-003 | Pass | Ready for Refinement | Release 1.1
US-004 | E2 | As a promise owner, I want detected commitment text and evidence highlighted so that I understand why the AI created the item. | Must | 5 | FR-006 | Pass | Ready for Refinement | MVP
US-005 | E2 | As a reviewer, I want low-confidence candidates routed to a queue so that false positives do not affect accountability metrics. | Must | 8 | FR-007 | Pass | Ready for Refinement | MVP
US-006 | E2 | As an employee, I want relative dates such as 'next Friday' resolved in my time zone so that due dates are accurate. | Must | 8 | FR-011 | Pass | Ready for Refinement | MVP
US-007 | E2 | As a data scientist, I want corrections captured with model version and reason so that I can evaluate systematic error patterns. | Should | 5 | FR-025 | Pass | Ready for Refinement | Release 1.1
US-008 | E3 | As an employee, I want to confirm or reject ownership so that the ledger reflects true accountability. | Must | 5 | FR-010 | Pass | Ready for Refinement | MVP
US-009 | E3 | As a manager, I want to reassign a promise with reason and audit trail so that coverage changes remain transparent. | Must | 5 | FR-014 | Pass | Ready for Refinement | MVP
US-010 | E3 | As a promise owner, I want to request a new due date so that legitimate delays are documented rather than hidden. | Should | 5 | FR-015 | Pass | Ready for Refinement | Release 1.1
US-011 | E3 | As an employee, I want to mark a promise fulfilled and attach completion evidence so that closure is verifiable. | Must | 5 | FR-013 | Pass | Ready for Refinement | MVP
US-012 | E3 | As an employee, I want to dispute an incorrectly attributed promise so that it is excluded from punitive metrics pending review. | Must | 8 | FR-026 | Pass | Ready for Refinement | MVP
US-013 | E4 | As an employee, I want reminders timed to urgency and my preferences so that I receive useful rather than repetitive notifications. | Must | 5 | FR-016 | Pass | Ready for Refinement | MVP
US-014 | E4 | As a department head, I want high-risk overdue commitments escalated automatically so that critical failures are addressed early. | Must | 8 | FR-017 | Pass | Ready for Refinement | MVP
US-015 | E4 | As an employee, I want to update a promise directly from a Slack or Teams card so that I do not lose workflow context. | Should | 8 | FR-018 | Pass | Ready for Refinement | Release 1.1
US-016 | E5 | As a manager, I want saved compound filters so that I can reuse my weekly risk review view. | Must | 5 | FR-019 | Pass | Ready for Refinement | MVP
US-017 | E5 | As a promise owner, I want a unified timeline of messages and status events so that I can reconstruct decisions. | Must | 5 | FR-020 | Pass | Ready for Refinement | MVP
US-018 | E6 | As a COO, I want enterprise completion, aging and SLA trends so that I can identify execution risk. | Must | 8 | FR-021 | Pass | Ready for Refinement | MVP
US-019 | E6 | As a team lead, I want a workload and bottleneck dashboard so that I can balance ownership and remove blockers. | Must | 8 | FR-022 | Pass | Ready for Refinement | MVP
US-020 | E6 | As an employee, I want a personal commitment queue so that I can prioritize what I owe and what is due next. | Must | 5 | FR-023 | Pass | Ready for Refinement | MVP
US-021 | E6 | As a compliance manager, I want a monthly evidence report so that I can demonstrate follow-up on regulated commitments. | Should | 5 | FR-024 | Pass | Ready for Refinement | Release 1.1
US-022 | E7 | As a privacy officer, I want regional retention and legal hold rules so that content is processed lawfully. | Must | 13 | FR-029 | Pass | Ready for Refinement | MVP
US-023 | E7 | As a compliance investigator, I want audited access to event history so that investigations are complete and controlled. | Must | 8 | FR-028 | Pass | Ready for Refinement | MVP
US-024 | E8 | As a platform admin, I want to manage SLAs, thresholds, calendars and templates without code changes so that business policy can evolve safely. | Must | 8 | FR-030 | Pass | Ready for Refinement | MVP

## RTM
fr_id | br_id | epic_id | user_stories | data_objects | test_cases | dashboard_or_report | status
FR-001 | BR-001 | E1 | US-001 | source_system, conversation, message, ingestion_checkpoint | TC-001, TC-002 | Integration Health | Traced
FR-002 | BR-001 | E1 | US-002 | source_system, conversation, message, ingestion_checkpoint | TC-003 | Integration Health | Traced
FR-003 | BR-001 | E1 | US-003 | source_system, conversation, message, ingestion_checkpoint | TC-004 | Integration Health | Traced
FR-004 | BR-001 | E1 | Covered by epic-level design | source_system, conversation, message, ingestion_checkpoint | TC-005 | Integration Health | Traced
FR-005 | BR-002 | E2 | Covered by epic-level design | promise_candidate, model_inference, person_alias, feedback_label | See NFR / integration suite | AI Quality | Traced
FR-006 | BR-002 | E2 | US-004 | promise_candidate, model_inference, person_alias, feedback_label | TC-006, TC-007 | AI Quality | Traced
FR-007 | BR-002 | E2 | US-005 | promise_candidate, model_inference, person_alias, feedback_label | TC-008, TC-009 | AI Quality | Traced
FR-008 | BR-003 | E3 | Covered by epic-level design | promise, promise_status_history, promise_owner_history | See NFR / integration suite | Promise Ledger | Traced
FR-009 | BR-004 | E2 | Covered by epic-level design | promise_candidate, model_inference, person_alias, feedback_label | TC-010 | AI Quality | Traced
FR-010 | BR-004 | E3 | US-008 | promise, promise_status_history, promise_owner_history | TC-011 | Promise Ledger | Traced
FR-011 | BR-005 | E2 | US-006 | promise_candidate, model_inference, person_alias, feedback_label | TC-012 | AI Quality | Traced
FR-012 | BR-005 | E3 | Covered by epic-level design | promise, promise_status_history, promise_owner_history | TC-013 | Promise Ledger | Traced
FR-013 | BR-006 | E3 | US-011 | promise, promise_status_history, promise_owner_history | TC-014, TC-015 | Promise Ledger | Traced
FR-014 | BR-006 | E3 | US-009 | promise, promise_status_history, promise_owner_history | TC-016 | Promise Ledger | Traced
FR-015 | BR-006 | E3 | US-010 | promise, promise_status_history, promise_owner_history | TC-017 | Promise Ledger | Traced
FR-016 | BR-007 | E4 | US-013 | notification, escalation_event, notification_preference | TC-018, TC-019 | Risk & Escalation | Traced
FR-017 | BR-008 | E4 | US-014 | notification, escalation_event, notification_preference | TC-020 | Risk & Escalation | Traced
FR-018 | BR-007 | E4 | US-015 | notification, escalation_event, notification_preference | TC-021 | Risk & Escalation | Traced
FR-019 | BR-009 | E5 | US-016 | search_index, conversation_event | TC-022 | Search / Timeline | Traced
FR-020 | BR-003 | E5 | US-017 | search_index, conversation_event | TC-023 | Search / Timeline | Traced
FR-021 | BR-010 | E6 | US-018 | fact_promise, fact_promise_event, dimensions and aggregates | TC-024 | Executive and Department Dashboards | Traced
FR-022 | BR-010 | E6 | US-019 | fact_promise, fact_promise_event, dimensions and aggregates | See NFR / integration suite | Executive and Department Dashboards | Traced
FR-023 | BR-010 | E6 | US-020 | fact_promise, fact_promise_event, dimensions and aggregates | See NFR / integration suite | Executive and Department Dashboards | Traced
FR-024 | BR-011 | E6 | US-021 | fact_promise, fact_promise_event, dimensions and aggregates | TC-025 | Executive and Department Dashboards | Traced
FR-025 | BR-012 | E2 | US-007 | promise_candidate, model_inference, person_alias, feedback_label | See NFR / integration suite | AI Quality | Traced
FR-026 | BR-012 | E3 | US-012 | promise, promise_status_history, promise_owner_history | TC-026 | Promise Ledger | Traced
FR-027 | BR-013 | E7 | Covered by epic-level design | audit_event, access_policy, retention_policy, legal_hold | TC-027 | Compliance Dashboard | Traced
FR-028 | BR-014 | E7 | US-023 | audit_event, access_policy, retention_policy, legal_hold | TC-028 | Compliance Dashboard | Traced
FR-029 | BR-015 | E7 | US-022 | audit_event, access_policy, retention_policy, legal_hold | TC-029 | Compliance Dashboard | Traced
FR-030 | BR-018 | E8 | US-024 | configuration_version, reference_data, feature_flag | TC-030 | Admin Portal | Traced

## Test_Cases
test_case_id | requirement_id | scenario | precondition | expected_result | test_type | status | severity
TC-001 | FR-001 | Register Slack connector with valid OAuth scopes | Valid tenant admin and approved app | Connector active; test event succeeds; scopes logged | System / Integration | Not Executed | Medium
TC-002 | FR-001 | Reject connector registration with excessive scope | Requested scope exceeds policy | Activation blocked; policy error and audit event created | Security | Not Executed | High
TC-003 | FR-002 | Process duplicate webhook event | Same source event ID submitted twice | One canonical message and no duplicate promise created | Integration | Not Executed | Medium
TC-004 | FR-003 | Replay failed checkpoint range | Known failed ingestion checkpoint | Missing messages recovered; downstream processing idempotent | Recovery | Not Executed | Medium
TC-005 | FR-004 | Normalize threaded Slack message | Valid source payload | Canonical conversation/message fields populated correctly | Data | Not Executed | Medium
TC-006 | FR-006 | Extract explicit promise | Message: I will send the report by Friday | Promise text, owner, deadline and confidence returned | AI | Not Executed | Medium
TC-007 | FR-006 | Do not create promise from informational statement | Message: The report was sent Friday | No commitment candidate created | AI | Not Executed | Medium
TC-008 | FR-007 | Auto-create high confidence candidate | Confidence above auto-create threshold | Promise created and marked human-unconfirmed per policy | Functional | Not Executed | Medium
TC-009 | FR-007 | Route medium confidence candidate | Confidence in review band | Candidate appears in review queue only | Functional | Not Executed | Medium
TC-010 | FR-009 | Resolve named owner | Message names active directory user | Correct employee ID assigned with evidence | AI / Data | Not Executed | Medium
TC-011 | FR-010 | Owner rejects attribution | Detected owner selects Reject and reason | Promise enters disputed/review state; audit captured | UAT | Not Executed | Medium
TC-012 | FR-011 | Resolve next Friday across time zone | User locale and business calendar configured | Due timestamp resolves to correct local business date | Functional | Not Executed | Medium
TC-013 | FR-012 | Handle ambiguous phrase soon | No deterministic date available | No enforceable due date; confirmation requested | Functional | Not Executed | Medium
TC-014 | FR-013 | Complete open promise | Authorized owner with open item | State becomes Fulfilled; completed timestamp recorded | UAT | Not Executed | Medium
TC-015 | FR-013 | Block invalid state transition | Cancelled item changed directly to Fulfilled | Request rejected according to transition matrix | Negative | Not Executed | Medium
TC-016 | FR-014 | Reassign with reason | Manager selects new owner and reason | New owner notified; history stores before/after values | UAT | Not Executed | Medium
TC-017 | FR-015 | Request due date extension | Owner provides proposed date and reason | Approval route applied; SLA clock handled per policy | UAT | Not Executed | Medium
TC-018 | FR-016 | Send due-soon reminder | High-priority item within warning window | One reminder sent through preferred channel | Integration | Not Executed | Medium
TC-019 | FR-016 | Suppress duplicate reminder | Reminder already sent within suppression period | No second notification generated | Negative | Not Executed | Medium
TC-020 | FR-017 | Escalate critical overdue item | Critical item overdue beyond threshold | Escalation event and manager notification created | UAT | Not Executed | Medium
TC-021 | FR-018 | Complete from Teams card | Valid signed action payload | Promise completed and card refreshed | Integration | Not Executed | Medium
TC-022 | FR-019 | Search with text and department filter | Authorized user | Results match both conditions within 2 seconds P95 target | Performance | Not Executed | Medium
TC-023 | FR-020 | Render conversation timeline | Promise with messages and history | Chronological events display with evidence links | UAT | Not Executed | Medium
TC-024 | FR-021 | Drill from executive KPI | Executive selects overdue rate | Authorized department/project detail opens with same filter context | UAT | Not Executed | Medium
TC-025 | FR-024 | Deliver scheduled monthly report | Valid schedule and recipients | Report generated, access checked and delivery logged | Reporting | Not Executed | Medium
TC-026 | FR-026 | Disputed item excluded from score | Promise in active dispute | Accountability KPI excludes item and labels exclusion | Data / UAT | Not Executed | Medium
TC-027 | FR-027 | Enforce source row security | User lacks access to original conversation | Promise and source evidence are not visible | Security | Not Executed | High
TC-028 | FR-028 | Audit export requires purpose | Compliance user omits purpose code | Export blocked and attempt logged | Compliance | Not Executed | High
TC-029 | FR-029 | Apply retention deletion | Record reaches retention expiration without hold | Content deleted/anonymized per policy; tombstone audit retained | Compliance | Not Executed | High
TC-030 | FR-030 | Update SLA reference data | Authorized admin changes High target 48 to 36 hours | Versioned configuration effective from chosen date; no retroactive corruption | UAT | Not Executed | Medium

## Risk_Register
risk_id | category | risk | probability | impact | score | mitigation | owner
R-001 | Privacy | Employees perceive the platform as surveillance rather than workflow assistance. | High | High | 20 | Purpose limitation, transparent evidence, dispute process, aggregate reporting thresholds, works council/legal review. | Privacy Officer
R-002 | AI Quality | False positives create notification fatigue and undermine trust. | High | High | 20 | Confidence bands, human review, precision-first MVP, user correction telemetry, source-specific thresholds. | ML Lead
R-003 | Integration | API limits, token expiry or schema changes interrupt ingestion. | Medium | High | 15 | Durable checkpoints, replay, token alerts, contract tests, vendor change monitoring. | Integration Lead
R-004 | Security | Sensitive content is exposed beyond original source permissions. | Low | Critical | 20 | Permission mirroring, row-level security, least privilege, penetration tests, break-glass controls. | CISO Delegate
R-005 | Adoption | Users ignore or reject AI-detected promises. | Medium | High | 15 | Pilot champions, low-friction confirmation, personal value features, adoption analytics, targeted training. | Change Lead
R-006 | Data | Identity aliases and team references resolve to the wrong owner. | Medium | Medium | 12 | Directory mastering, alias stewardship, confidence indicators, owner confirmation. | Data Steward
R-007 | Legal | Cross-border transfer or retention violates regional policy. | Low | Critical | 20 | Regional processing, policy engine, legal holds, DPIA, configurable retention. | Legal Counsel
R-008 | Performance | Search and analytics degrade at enterprise message volume. | Medium | Medium | 12 | Partitioning, asynchronous enrichment, search index, materialized aggregates, load testing. | Solution Architect
R-009 | Change | Scope expands into general project management and delays MVP. | High | Medium | 16 | Explicit out-of-scope, product principles, change control and value-based backlog. | Product Owner
R-010 | Analytics | Individual accountability metrics are misused without context. | Medium | High | 15 | Contextual exclusions, minimum sample sizes, disputes, governance, no automated performance action. | HR & Privacy

## RAID_Log
raid_id | type | description | owner | due_date | status | impact
A-001 | Assumption | Source APIs and enterprise identity sandbox are available by architecture sprint. | Program Manager | 2026-09-04 | Open | Could delay connector development.
A-002 | Assumption | Pilot departments permit processing of internal business communications under approved policy. | Privacy Officer | 2026-09-18 | Open | Pilot scope may need reduction.
I-001 | Issue | Gmail delegated access pattern requires additional security exception review. | Security Lead | 2026-09-11 | In Progress | Email integration could move to Release 1.1.
D-001 | Dependency | Enterprise directory alias cleanup must complete before owner resolution UAT. | Data Steward | 2026-12-04 | Open | Owner matching precision risk.
D-002 | Dependency | BI gateway and certified workspace must be provisioned for Power BI dashboards. | BI Platform Owner | 2026-12-18 | Open | Dashboard UAT delay.
R-001 | Risk | Employee surveillance perception reduces adoption. | Change Lead | 2027-02-08 | Mitigating | Low confirmation and usage rates.
R-002 | Risk | Model precision below 0.88 at pilot entry. | ML Lead | 2027-01-22 | Mitigating | Review workload and trust risk.
I-002 | Issue | Teams adaptive card action callback is blocked in one network segment. | Integration Lead | 2026-12-11 | Open | Teams update-in-place feature at risk.

## Timeline
phase | start | end | duration_weeks | deliverables
Discovery & Mobilization | 2026-08-03 | 2026-08-21 | 3 | Charter, stakeholder map, baseline metrics, scope, DPIA kickoff
Requirements & Experience Design | 2026-08-24 | 2026-09-25 | 5 | BRD, FRD, process models, wireframes, backlog, RTM
Architecture & Data Foundation | 2026-09-14 | 2026-10-09 | 4 | Architecture, canonical model, security design, connectors framework
MVP Build | 2026-10-12 | 2026-12-18 | 10 | Slack, Teams, Gmail; AI extraction; ledger; reminders; dashboards
System Test & UAT | 2027-01-04 | 2027-02-05 | 5 | SIT, performance/security tests, UAT, defect closure
Pilot & Hypercare | 2027-02-08 | 2027-03-12 | 5 | 500-user pilot, model tuning, adoption support, value measurement
Enterprise Release 1.0 | 2027-03-15 | 2027-04-16 | 5 | 3,500-user rollout, report automation, operating model
Release 1.1 | 2027-04-19 | 2027-06-11 | 8 | Zoom, Jira, CRM/support integrations, predictive risk, advanced analytics

## Sprint_Plan
sprint | start | end | goal | stories | capacity_points | planned_points
Sprint 1 | 2026-10-12 | 2026-10-23 | Ingestion foundation and canonical message model | US-001, US-002 | 34 | 16
Sprint 2 | 2026-10-26 | 2026-11-06 | Promise extraction and confidence policy | US-004, US-005 | 34 | 13
Sprint 3 | 2026-11-09 | 2026-11-20 | Owner and deadline resolution | US-006, US-008 | 34 | 13
Sprint 4 | 2026-11-23 | 2026-12-04 | Ledger lifecycle and evidence | US-009, US-011, US-017 | 34 | 15
Sprint 5 | 2026-12-07 | 2026-12-18 | Reminders, escalations and notification actions | US-013, US-014, US-015 | 34 | 21
Sprint 6 | 2026-12-21 | 2027-01-01 | Search, personal queue and manager dashboard | US-016, US-019, US-020 | 34 | 18
Sprint 7 | 2027-01-04 | 2027-01-15 | Executive analytics and scheduled reporting | US-018, US-021 | 34 | 13
Sprint 8 | 2027-01-18 | 2027-01-29 | Privacy, audit and retention controls | US-022, US-023 | 34 | 21
Sprint 9 | 2027-02-01 | 2027-02-12 | Administration, hardening and accessibility | US-024 | 34 | 8
Sprint 10 | 2027-02-15 | 2027-02-26 | End-to-end stabilization and release candidate | US-003, US-007, US-010, US-012 | 34 | 23

## Change_Requests
change_id | request | requestor | impact | decision | rationale
CR-001 | Add WhatsApp Business ingestion to MVP | Sales | High privacy review, unsupported enterprise archive pattern, +8 weeks | Rejected / Release TBD | Not aligned with approved corporate communication channels.
CR-002 | Include employee performance rating based on broken promises | Operations Leader | Material HR, legal and ethics risk | Rejected | OpenLoop supports workflow accountability, not automated employment decisions.
CR-003 | Add Jira issue creation from confirmed promises | Engineering | Moderate scope; 13 story points; useful adoption benefit | Approved for Release 1.1 | Fits integration strategy after ledger stability.
CR-004 | Increase pilot from 500 to 1,200 users | Executive Sponsor | Additional support and capacity testing | Conditionally Approved | Proceed if model precision and P95 latency pass entry criteria.

## Defect_Log
defect_id | summary | severity | environment | linked_test | status | root_cause | resolution
DEF-001 | Relative date 'next Monday' resolves incorrectly near midnight UTC | High | SIT | TC-012 | Fixed | Locale conversion applied after date parsing | Apply user time zone before business-date resolution.
DEF-002 | Duplicate reminder sent after notification retry | Medium | SIT | TC-019 | Retest | Idempotency key omitted channel | Use promise + policy + window + channel key.
DEF-003 | Manager can see source snippet after source access revoked | Critical | Security Test | TC-027 | Fixed | Cached evidence bypassed ACL refresh | Real-time authorization check and cache invalidation.
DEF-004 | Keyboard focus skips confidence explanation tooltip | Medium | Accessibility | NFR-009 | Open | Non-focusable icon control | Replace with accessible button and ARIA description.
DEF-005 | Executive trend report excludes reassigned fulfilled promises | High | UAT | TC-024 | Fixed | Latest owner join used inner join on reassignment history | Use effective-dated owner bridge and left join.

## Executive_Control
OPENLOOP ¦ Requirements & Delivery Control Center
Control Metric | Value |  | Priority | BR Count | FR Count
Business Requirements | 18 |  | Must | 15 | 25
Functional Requirements | 30 |  | Should | 3 | 5
Nonfunctional Requirements | 15 |  | Could | 0 | 0
User Stories | 24 |  | Won't | 0 | 0
Test Cases | 30 |  | Total | 18 | 30
RTM Rows Traced | 30
Open RAID Items | 6
Open Defects | 0
Governance Gate | Entry Criteria | Owner | Target | Status | Evidence
Requirements Baseline | BRD/FRD approved; RTM complete | Product Owner | 2026-09-25 | On Track | BRD, FRD, RTM
Architecture Approval | Security, privacy and data design approved | Solution Architect | 2026-10-09 | On Track | Architecture Decision Records
MVP Code Complete | Must-have stories complete; Sev-1/2 defects closed | Engineering Lead | 2026-12-18 | Planned | Build and CI evidence
UAT Entry | SIT pass >=95%; performance/security gates met | QA Lead | 2027-01-18 | Planned | Test summary
Pilot Entry | Precision >=0.88; privacy and support sign-off | Product Owner | 2027-02-08 | Planned | Model card and readiness checklist
Enterprise Release | Pilot adoption >=65%; no critical incidents | Executive Sponsor | 2027-03-15 | Planned | Value and operational readiness report
Value Review | Benefits validated with finance | COO / Finance | 2027-06-30 | Planned | Benefits realization report